## Product_Backlog
Product Name:
Team ID:

Name:	Zackery Gualandi
Initials:	ZAG
Student ID:	1001448365

(Additional names for teams only)
Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Name:
Initials:
Student ID:

Total Features	36	Status	Sprint Ends
Sprint 1 Left	36	Completed	Oct 06
Sprint 2 Left	36	Completed	Oct 13
Sprint 3 Left	36	Completed	Oct 20
Sprint 4 Left	36	Due	Oct 27
Sprint 5 Left	36	Due	Nov 03
Sprint 6 Left	36	Due	Nov 10
Sprint 7 Left	35	Due	Nov 17
Sprint 8 Left	35	Due	Nov 22

					Note: Priority of unfinished Features is subject to change at the end of each sprint at the whim of the Product Owner
					Additional features may be proposed by the student / team but must be approved by the Product Owner in writing
Feature ID	Prio	Status	Sprint #	Team Size	As a...	I want to...	So that...	Notes
	1			1	All	open a GUI main window	I can interact with RRS Manager with my mouse	No menu required here – run program, create a part
	2			1	PM	create robot parts	I can define robot models	No menu required here – run program, create a part
	3			1	PM	create robot parts via GUI dialogs	I can define robot models	An fl_input centric approach is OK initially, but a custom dialog is worth bonus points (perhaps Create > Robot Part)
	4			1	PM	define new robot models	RRS can sell them to our Beloved Customers	Menu needed – create parts, then create a robot model
	5			1	PM	define new robot models via GUI dialogs	RRS can sell them to our Beloved Customers	Similar to robot parts (perhaps Create > Robot Model)
	6			1	BC	browse a catalog of robots	I can buy one or more robots	Need to list robots models, then list parts in selected model
	7			1	BC	browse a catalog of robots via a GUI report	I can buy one or more robots	A text output is OK initially, but an attractive HTML-like output is desired (perhaps (Report > All Robot Models)
	8			1	BC	see pictures of the robots in the GUI catalog	I can see what I'm buying	Add picture when defining robot model, and show it in the robot model report
	9			1	SA	create a robot order for a Customer	I can sell robots and thus do my job well	Select robot model and quantity, show details with total price
	10			1	PB	Create a new Beloved Customer via GUI	I can keep track of who's buying our products	The usual name, address, phone number, and email address (perhaps Create > Customer)
	11			1	PB	Create a new Sales Associate via GUI	I can keep track of my employees' performance	Name and employee number at a minimum (perhaps Create > Sales Associate)
	12			1	SA	Create a robot order for a Customer via GUI	I can sell robots and thus do my job well
	13			2	PB	ensure persistence of the RRS data	we don't lose orders or historical data	Write the data to the default filename and reload it next time the program runs
	14			2	PB	allow the users to save data explicitly via GUI	we can save data without exiting the program	Write the data to the default filename on command (perhaps File > Save to the default filename)
	15			2	PB	allow the users to load data explicitly via GUI	we can manage multiple stores in different files	Read the data from a user-selected file on command (perhaps File > Open)
	16			2	PB	allow the users to save data to a specified name via GUI	we can manage multiple stores in different files	Write the data to a user-selected file on command and make that fie the default (perhaps File > Save As)
	23			2	PB / SA	view a list of orders per SA	I can estimate the value of employees / / I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
	24			2	PB / SA	view a report of orders per SA in the GUI	I can estimate the value of employees / / I can justify a raise	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	17			3	All	enable basic login by role and customize the GUI	we don't have options that don't apply to our roles	User ID might be “sa” for Sales associate with a default password, via a dialog on launch (i.e., in main()),and then make inapplicable menu items inactive – keep it simple
	18			3	All	enable copy and paste from text fields	we can save typing	Just implement this where the toolkit supports it – not all text widgets do, but it's easy where it's supported

	21			3	BC	view my bill	I can pay for my robots	Show a BC invoice. Actual payment is outside the scope of this project
	22			3	BC	view my bill (invoice) in the GUI	I can pay for my robots	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Invoice)
	25			3	BC	view my orders	see what I have coming to me	Show list of orders for a BC with total price, then list details of selected order
	26			3	BC	view my orders in the GUI	see what I have coming to me	A basic text report is fine initially, but a more attractive HTML report is desired (perhaps Report > Orders by Customer)
	27			4	SA	view a sales report	I can justify a raise	Show list of orders for an SA with total price, then list details of selected order
	28			4	SA	view a sales report in the GUI	I can justify a raise	A basic text report is fine (perhaps Report > Orders by Sales Associate)
	19			4	PB	view a list of orders	I can manage the company	Show list of every order with total price, then list details of selected order
	20			4	PB	view a report of all orders in the GUI	I can manage the company	A basic text report is fine (perhaps Report > All Orders)
	29			4	All	Add multi-level undo	Worry less about making mistakes	This would be for each Create event (e.g., a new Customer) only (perhaps Edit > Undo)
	30			4	BC	see a pie chart of a model's component costs	I can decide if I want a different model	Consider using Fl_Chart, q.v., (perhaps Report > Robot Model Cost Breakdown)
	31			Bonus	SA	create a bulk (2+) order for Customer via GUI	avoid proliferation of orders and paperwork	Allow more than one robot model (with respective quantity) on a single order
	32			Bonus	PM	hide robot parts via GUI	obsolete parts aren't accidentally used	Mark robot parts as “obsolete” and don't allow adding them to new robot models
	33			Bonus	PM	hide robot models via GUI	obsolete robots aren't ordered	Mark robot models as “obsolete” and don't allow adding them to new orders
	34			Bonus	SA	save a draft order and return to it later via GUI	I can multi-task between indecisive customers	Save an order that hasn't been complete, and allow SA to resume work on it later
	35			Extreme Bonus	BC	browse and order robots over the web	I don't have to talk to the Sales Associates!	(Probably can't address until Homework #6)
	36			Extreme Bonus	PB	avoid any delays in the RRS web software	my SA team is at maximum productivity	This likely means using threads for key processes / (Probably can't address until Homework #6)
Product Backlog Burn Chart
Features Remaining at Start of Sprint
Sprints

## Sprint_NN_Backlog
Sprint #					*** Example Only – Set up a tab for EACH SPRINT ***
Start on
End on
Demo on

Total Tasks	23
Day 1 Left	23
Day 2 Left	23
Day 3 Left	23
Day 4 Left	23
Day 5 Left	23
Day 6 Left	23
Day 7 Left	23

Task ID	Feature ID	Category	Type	Assigned To	Description	Status	Notes
Sprint Burn Chart
Days
Tasks